## Read Me
Baumarkt-Buddy – Release Planning Workbook
Source: requirements/baumarkt-buddy-product-requirements.md v1.0 · Draft 23 Oct 2026 · Owner: Quality & Responsible AI
Purpose
Plan the product in 3 releases: select functional, safety, non-functional and data requirements per release, the design components needed to build them, and the release-blocking tests that verify each release.
Releases (course scope)
| R1 – MVP / Pitch demo | 2-week sprint (19 Oct – ~1 Nov 2026). One safe end-to-end flow: text/template -> questions -> validated shopping list with aisle. Built and tested.
| R2 – Extended MVP | Planned (roadmap only). More templates, explanations, alternatives, owned items, offline checklist, assembly guide.
| R3 – Pilot-ready | Planned (roadmap only). Photo and voice entry, real store data, store search, scanner, associate hand-off, monitoring.
| Beyond | Not planned in the 3 releases (reservation, multi-retailer).
METHOD 1 – Team selection (bottom-up)
| Sheets | M1 Requirements · M1 Design Components · M1 Traceability
| Step 1 | Everyone reads M1 Requirements (68 items: 24 FR, 10 SR, 11 NFR, 7 DR, 14 release-blocking tests).
| Step 2 | In the team meeting, fill the yellow columns: Team MoSCoW (Must/Should/Could/Won't) and Team release (R1/R2/R3/Beyond).
| Step 3 | M1 Design Components then shows automatically which components are needed and in which release (earliest release of any linked requirement).
| Step 4 | Use M1 Traceability to check that every selected requirement has its components and that every release-blocking test is in the same release as its feature.
| Result | The team's own release plan. Good for discussion and buy-in, but slower and depends on the team's judgement.
METHOD 2 – Claude's proposal (top-down, recommended)
| Technique | Goal-driven release slicing with MoSCoW per release + walking skeleton + V-model exit gates.
| Step 1 · Release goal | Define ONE goal per release (see above). The goal is the filter for everything else.
| Step 2 · MoSCoW per release | For each requirement ask: is it needed for this release's goal? Must = goal fails without it · Should = important, not vital · Could = if time allows · Won't = moved to a later release.
| Step 3 · Safety rule | Every safety requirement and release-blocking test that applies to a feature in the release is automatically Must in that release. Safety is never negotiated down.
| Step 4 · Walking skeleton | R1 builds a thin slice through ALL 5 architecture layers (UI, orchestrator, AI, deterministic gates, data). Later releases widen layers, not add new ones.
| Step 5 · Dependencies | A requirement cannot be earlier than the components and data it needs (e.g. assembly guide needs manufacturer data).
| Step 6 · Capacity check | Musts should be about 60 % of the release effort; Should/Could fill the rest. If Musts exceed capacity, reduce scope (e.g. fewer templates), not safety.
| Step 7 · Exit gate | A release is done only when its release-blocking tests pass (V&V) and its validation KPI is met (user test).
| Roadmap sheet | Roadmap Components: design components per release with MoSCoW priority and source priority (P0/P1/P2).
| Sheets | M2 Proposal (one row per requirement with release, MoSCoW, rationale, team accept/change) · M2 Components by Release · M2 Release Plan (counts + gates).
How to use the two methods together
1) Each member fills Method 1 alone (10 min). 2) Compare with Method 2 in the meeting. 3) Discuss only the rows where they differ. 4) Record the decision in M2 Proposal -> 'Team decision'.
Legend
| Yellow cells | Team input (drop-down lists).
| Source priority | P0 = MVP mandatory · P1 = pilot · P2 = later · Gate = release-blocking test (as in the requirements file).
| Example (Method 1 row) | FR-05 · Team MoSCoW = Must · Team release = R1 · Owner = Quality · Comment = 'max. 3 questions, wall type + load'
| Note | FR-02, FR-03, FR-04, FR-24, SR-02, SR-07, SR-10 contain several parts. Method 2 rationale says which part goes into which release.

## M1 Requirements
Method 1 – All requirements (fill yellow columns as a team)
68 items from requirements v1.0 · filter with the arrows in row 4
ID | Type | Category | Requirement | Acceptance criterion / verification | Source priority | Source § | Related design components | Team MoSCoW | Team release | Owner | Team comment | Release no. (auto)
FR-01 | Functional | Project lifecycle | Create, save, resume and delete a project | Returning user resumes the last confirmed state; deletion status is reported. | P0 | §4 | DC-13, DC-14, DC-15
FR-02 | Functional | Project entry | Accept a free-text project description and multiple role-labelled photos | Photo role is explicit (reference, room/installation area, owned item); reference and room photos are not silently treated as the same scene. | P0 | §4 | DC-01, DC-09, DC-17, DC-21
FR-03 | Functional | Project entry | Classify project intent and extract candidate objects/visible labels | At least 8 of 10 supported intent prompts are correctly classified in the project benchmark; observations retain source, uncertainty and confirmation status. | P0 | §4 | DC-17, DC-21, DC-02
FR-04 | Functional | Clarification & facts | Capture measurements, units, constraints and owned items | Critical dimensions and load are user-confirmed; unit conflicts block product matching; uncertain owned items are not treated as suitable. | P0 | §4 | DC-02, DC-23, DC-29
FR-05 | Functional | Clarification & facts | Ask dependency-aware follow-up questions | Ask no more than three at a time; allow skips; missing safety-critical substrate/load facts block final fixing selection. | P0 | §4 | DC-03, DC-18, DC-23, DC-32
FR-06 | Functional | Planning | Generate a structured bill of materials (BOM) | Separate materials, consumables, tools and PPE; show role, specification, quantity basis and dependencies; derive quantities from confirmed dimensions; target under 5 seconds for a bounded plan. | P0 | §4 | DC-19, DC-24, DC-32, DC-04
FR-07 | Functional | Planning | Reconcile suitable owned items against the BOM | Deduct only confirmed suitable quantities; mark unknown/uncertain items for identification. | P0 | §4 | DC-29, DC-02
FR-08 | Functional | Validation | Match exact catalogue products and variants | Each recommended item maps to a catalogue record and identifiable variant; the model cannot invent product names, SKUs or prices. | P0 | §4 | DC-25, DC-24, DC-30
FR-09 | Functional | Validation | Validate product and component compatibility | Check relevant dimensions, material, system, pack quantity and manufacturer-supported constraints; retain evidence for each check. | P0 | §4 | DC-24, DC-33, DC-34
FR-10 | Functional | Validation | Explain recommendations and unresolved facts | User can see why an item fits, which facts support it and what remains unverified. | P0 | §4 | DC-20, DC-04, DC-34
FR-11 | Functional | Shopping | Show price, availability and store information | Display price, tax/pack basis, stock status, source and retrieval time; unknown, stale and out-of-stock are distinct. Mock values are labelled as mock. | P0 | §4 | DC-04, DC-31, DC-35
FR-12 | Functional | Shopping | Offer feasible basket options and alternatives | Where supported catalogue alternatives exist, show compatible lower-cost or premium choices; enforce hard constraints and update totals immediately. | P0 | §4 | DC-28, DC-24, DC-04
FR-13 | Functional | Shopping | Support store search and retailer hand-off | Postcode works if location permission is denied; retailer hand-off does not imply reservation or purchase. | P0 | §4 | DC-12, DC-40
FR-14 | Functional | Shopping | Provide an offline project checklist | A saved list remains readable without network; stock claims are marked stale/unavailable. | P0 | §4 | DC-06, DC-15
FR-15 | Functional | Safety UX | Present safety stops and escalation | Model wording cannot dismiss a safety block; offer a store-associate or professional hand-off where appropriate. | P0 | §4 | DC-05, DC-22, DC-14
FR-16 | Functional | Assembly | Link assembly steps to reviewed sources | Applicable product/manual revision is identifiable; manufacturer warnings and stop conditions are preserved. | P0 | §4 | DC-08, DC-33, DC-32
FR-17 | Functional | Shopping | Export and share a project summary | User receives a readable export; sharing includes only selected information. | P0 | §4 | DC-07
FR-18 | Functional | Shopping | Show verified aisle/zone/rack locations | Location matches selected branch and map revision; otherwise show an honest fallback. | P1 | §4 | DC-31, DC-35, DC-04
FR-19 | Functional | Shopping | Scan products during shopping | A different size or variant triggers mismatch detection and revalidation. | P1 | §4 | DC-11, DC-16, DC-24
FR-20 | Functional | Assembly | Track assembly and deviations | A changed component invalidates affected downstream steps. | P1 | §4 | DC-08, DC-16, DC-14
FR-21 | Functional | Integration | Support an approved reservation integration | Exact action is approved; retries cannot create duplicate external actions. | P1 | §4 | DC-40
FR-22 | Functional | Integration | Share a summary with a store associate | Only user-selected project information is shared. | P1 | §4 | DC-07, DC-40
FR-23 | Functional | Integration | Optimise baskets across retailers | Hard compatibility constraints remain enforced across split baskets. | P2 | §4 | DC-28, DC-40, DC-24
FR-24 | Functional | Project entry | Add voice interaction or room visualisation | Visualisation is labelled conceptual and cannot override measured dimensions. | P2 | §4 | DC-10, DC-17
SR-01 | Safety | Evidence | Separate visual guesses from user-confirmed facts and manufacturer-supported specifications. | Every fact carries a status (observed / user-confirmed / manufacturer-supported / unknown). | P0 | §6 | DC-02, DC-14, DC-23
SR-02 | Safety | Evidence | Never certify wall type, allowable load, concealed services or safe drilling locations from photos. A detector's negative result is not clearance to drill. | Verified by RB-02, RB-07. | P0 | §6 | DC-21, DC-23, DC-24
SR-03 | Safety | Mounting gate | Require confirmed substrate, fixing system, bracket geometry, intended loading and applicable installation conditions before a final mounting recommendation. | Verified by RB-01. | P0 | §6 | DC-23, DC-24, DC-32
SR-04 | Safety | Mounting gate | Do not calculate shelf capacity by adding nominal anchor ratings; rely on applicable system evidence or refer to a qualified person. | Rule engine contains no summation of plug ratings (code review + unit test). | P0 | §6 | DC-24, DC-33
SR-05 | Safety | Drilling | Describe detector capabilities and limitations for relevant hazards; do not imply every detector finds every pipe, especially plastic pipes. | Verified by RB-07. | P0 | §6 | DC-24, DC-05
SR-06 | Safety | Fail-safe | Inconclusive or missing evidence triggers a stop, not permission to proceed. | Verified by RB-01, RB-03. | P0 | §6 | DC-23, DC-14, DC-05
SR-07 | Safety | Evidence | Preserve manufacturer warnings, installation conditions and approved combinations; generated text cannot weaken them. | Verified by RB-08. | P0 | §6 | DC-33, DC-24, DC-04
SR-08 | Safety | Revalidation | Re-run safety and compatibility checks after changes to material, dimensions, load or product. | Verified by RB-04, RB-14. | P0 | §6 | DC-16, DC-14, DC-24
SR-09 | Safety | Scope | Exclude high-risk work from the supported flow and provide an appropriate professional hand-off. | 100 % of high-risk test prompts refused with hand-off; no BOM shown. | P0 | §6 | DC-22, DC-05
SR-10 | Safety | Governance | Qualified reviewers approve project templates and release-blocking test cases before public mounting guidance. | Template status 'reviewed' required before use. | P0 | §6 | DC-41, DC-32
NFR-01 | Non-functional | Usability | Mobile-first; core flow completable in under two minutes in usability testing without instructions. | Usability test: basic flow < 2 min without help. | P0 | §7 | DC-01, DC-04, DC-39
NFR-02 | Non-functional | Performance | Catalogue lookup under one second; bounded MVP list generation under five seconds. For a multi-step pilot plan, show progress and target under 60 s at p95. | Measured on test set. | P0 | §7 | DC-13, DC-24, DC-30
NFR-03 | Non-functional | Reliability | If the model fails, offer predefined project templates; recover partial state. Do not proceed when a required validation service fails. | Fault test: model down -> templates offered, no crash. | P0 | §7 | DC-13, DC-26, DC-14
NFR-04 | Non-functional | Privacy | GDPR principles; no mandatory login; minimise personal data sent to model providers; document retention, deletion and vendor handling. | Privacy checklist reviewed. | P0 | §7 | DC-37
NFR-05 | Non-functional | Transparency | Label AI-generated guidance; distinguish estimates, confirmed facts and verified specifications. Quantities are estimates unless validated. | UI check: AI notice and labels visible. | P0 | §7 | DC-04, DC-02, DC-36
NFR-06 | Non-functional | Security | Encryption, least privilege, upload scanning, tenant isolation, rate limits and redacted logs; restrict tools and outbound domains. | Security review. | P0 | §7 | DC-37
NFR-07 | Non-functional | Untrusted input | Treat retailer pages, uploaded images, OCR text and manuals as data, never as instructions to the system. | Verified by RB-09. | P0 | §7 | DC-27, DC-17
NFR-08 | Non-functional | Accessibility | Accessible contrast, scalable text, screen-reader labels and a non-map shopping route. | Accessibility check. | P0 | §7 | DC-39
NFR-09 | Non-functional | Language | German and English; metric consistency and dimensional calculations tested in both. | Tests run in DE and EN. | P0 | §7 | DC-36, DC-17, DC-18
NFR-10 | Non-functional | Maintainability | Catalogue and project-template data separate from code and replaceable by authorised APIs/feeds. | Code review: no product data in code. | P0 | §7 | DC-30, DC-32, DC-35
NFR-11 | Non-functional | Observability | Track unsupported requests, escalations, incidents, source failures, latency and cost per completed project. | Monitoring dashboard / log report. | P0 | §7 | DC-38, DC-34
DR-01 | Data | Catalogue | Product catalogue: curated mock JSON/CSV (~150-300 products across 5-10 project types); later authorised retailer PIM/API. | Mock values labelled; every product has variant, size, load, wall types. | P0 | §8 | DC-30
DR-02 | Data | Stock & price | Stock and price: static, clearly labelled mock values; later timestamped inventory source with agreed freshness policy. | Every value has source + time; mock labelled. | P0 | §8 | DC-35, DC-31
DR-03 | Data | Store layout | Store layout: one store with aisle/zone values only if verified; later branch-specific planogram source. | No aisle shown without a record. | P0 | §8 | DC-31
DR-04 | Data | Templates | Project templates: 5-10 reviewed templates with explicit quantity rules. | Each template has required facts, questions, quantity rules, review status. | P0 | §8 | DC-32, DC-41
DR-05 | Data | Model | Model: commercial multimodal model for bounded intent/extraction and clarification; schema-validated outputs. | All model outputs pass schema validation. | P0 | §8 | DC-17, DC-26
DR-06 | Data | Sharing | Sharing: link or PDF export; later retailer hand-off. | Export contains only selected data. | P0 | §8 | DC-07
DR-07 | Data | Evidence | Evidence registry: source and retrieval time for curated records; later version, licence and lineage. | Every check stored with rule, inputs, source, time. | P0 | §8 | DC-34
RB-01 | Release-blocking test | Safety | Unknown wall substrate blocks final anchor selection. | Test passes = no anchor shown. | Gate | §10 | DC-23, DC-24
RB-02 | Release-blocking test | Safety | Photo without scale does not produce exact dimensions. | Test passes = no exact dimension. | Gate | §10 | DC-09, DC-21, DC-23
RB-03 | Release-blocking test | Compatibility | Similar-looking but wrong screw/variant is detected or remains unresolved. | Test passes = mismatch flagged. | Gate | §10 | DC-24, DC-25
RB-04 | Release-blocking test | Safety | Increased intended load invalidates affected fixing decisions. | Test passes = BOM revalidated. | Gate | §10 | DC-16, DC-24
RB-05 | Release-blocking test | Data | Stale stock is labelled stale and offers a verification path. | Test passes = stale label shown. | Gate | §10 | DC-35, DC-04
RB-06 | Release-blocking test | Data | Missing map data never produces a fabricated aisle. | Test passes = 'ask staff' shown. | Gate | §10 | DC-31, DC-04
RB-07 | Release-blocking test | Safety | Detector limits do not create false clearance for drilling. | Test passes = warning always shown. | Gate | §10 | DC-24, DC-05
RB-08 | Release-blocking test | Safety | Manufacturer manual wins if it conflicts with generated text. | Test passes = manufacturer text shown. | Gate | §10 | DC-33, DC-24
RB-09 | Release-blocking test | Security | Malicious instructions embedded in product data are ignored as instructions. | Test passes = injection ignored. | Gate | §10 | DC-27
RB-10 | Release-blocking test | Integration | Retried checkout/reservation action cannot create duplicates. | Test passes = one action only. | Gate | §10 | DC-40
RB-11 | Release-blocking test | Shopping | Denied location permission leaves postcode search available. | Test passes = postcode works. | Gate | §10 | DC-12
RB-12 | Release-blocking test | Offline | Network loss leaves saved checklist readable and removes live-stock certainty. | Test passes = list readable, stock stale. | Gate | §10 | DC-06
RB-13 | Release-blocking test | Compatibility | Ambiguous pack quantity prevents a misleading basket total. | Test passes = total withheld/flagged. | Gate | §10 | DC-24, DC-28
RB-14 | Release-blocking test | Revalidation | A changed product during shopping triggers revalidation of affected assembly steps. | Test passes = steps invalidated. | Gate | §10 | DC-11, DC-16

## M1 Design Components
Method 1 – Design / architecture components
Release needed is calculated from the team's picks in M1 Requirements (earliest release of any linked requirement)
ID | Layer | Component | Type | Responsibility | Must NOT do | Source priority | # linked requirements | Release needed (from team picks) | Team comment
DC-01 | L1 Presentation | Project entry screen (text + template picker) | UI | Free-text entry and choice of project template; start/resume project | Show results before validation | P0 | 2 | not selected
DC-02 | L1 Presentation | Project summary & fact confirmation | UI | Show understood facts with status; user confirms/edits load, dimensions, wall type | Use unconfirmed facts | P0 | 5 | not selected
DC-03 | L1 Presentation | Clarification question UI | UI | Show max. 3 questions, allow skip | Ask more than 3 at once | P0 | 1 | not selected
DC-04 | L1 Presentation | BOM / shopping list view | UI | Materials, consumables, tools, PPE with quantity basis, price, stock, aisle/shelf, mock & AI labels | Display unvalidated items or invented aisles | P0, P1 | 10 | not selected
DC-05 | L1 Presentation | Safety banner & hand-off UI | UI | Refusal, safety-blocked and detector warnings; 'hire a professional / ask staff' | Be dismissible by AI text | P0 | 5 | not selected
DC-06 | L1 Presentation | Checklist & offline cache (PWA) | UI | Tick-off list, readable offline, stock marked stale | Claim live stock offline | P0 | 2 | not selected
DC-07 | L1 Presentation | Export / share module | UI | Link/PDF export of user-selected info | Share unselected data | P0, P1 | 3 | not selected
DC-08 | L1 Presentation | Assembly guide view | UI | Step-by-step guide linked to BOM and reviewed sources | Reference items not in BOM | P0, P1 | 2 | not selected
DC-09 | L1 Presentation | Photo capture & role labelling | UI | Upload photos with explicit role | Merge reference and room photos | P0 | 2 | not selected
DC-10 | L1 Presentation | Voice input (speech-to-text) | UI | Transcribe speech, show editable transcript | Use spoken values unconfirmed | P2 | 1 | not selected
DC-11 | L1 Presentation | Barcode / product scanner | UI | Scan product during shopping, detect mismatch | Accept a different variant silently | P1 | 2 | not selected
DC-12 | L1 Presentation | Store search (postcode / location) | UI | Find store by postcode or optional location | Block app if location denied | P0 | 2 | not selected
DC-13 | L2 Application | Orchestrator / flow controller | Code | Calls agents and gates in fixed order; handles retries/fallback | Skip a gate | P0 | 3 | not selected
DC-14 | L2 Application | Project state machine | Code | Draft -> Needs clarification -> ... ; exception states | Advance state after a failed call | P0, P1 | 7 | not selected
DC-15 | L2 Application | Project persistence | Code | Save/resume/delete (session -> local -> backend) | Require login | P0 | 2 | not selected
DC-16 | L2 Application | Revalidation trigger | Code | Detect change of material/dimension/load/product; invalidate dependent lines | Keep stale validation | P0, P1 | 5 | not selected
DC-17 | L3 AI (proposes) | Intake agent | AI | Classify intent; extract candidate facts (status = observed) | Decide products or safety | P0, P2 | 6 | not selected
DC-18 | L3 AI (proposes) | Clarification agent | AI | Phrase questions for missing facts (DE/EN) | Decide which facts are required | P0 | 2 | not selected
DC-19 | L3 AI (proposes) | Planner agent | AI | Propose BOM roles (board, bracket, plug, screw, tools, PPE) | Return product names or prices | P0 | 1 | not selected
DC-20 | L3 AI (proposes) | Explanation generator | AI | Explain why items fit and what is unverified, from evidence log | Weaken warnings | P0 | 1 | not selected
DC-21 | L3 AI (proposes) | Vision extraction agent | AI | Candidate objects/labels from photos | Certify wall type, load or dimensions | P0 | 4 | not selected
DC-22 | L4 Control (decides) | G0 Scope / high-risk filter | Code | Detect electrical, gas, load-bearing, plumbing, roof -> refuse | Be overridden by AI | P0 | 2 | not selected
DC-23 | L4 Control (decides) | G1 Required-facts check | Code | Template's safety facts confirmed? else ask / block | Accept 'observed' facts for safety | P0 | 8 | not selected
DC-24 | L4 Control (decides) | Rule engine (R-01...R-16) | Code | Variants, quantities, compatibility, load limits, detector/PPE rules | Sum anchor ratings; hold limits in prompts | P0, P1, P2 | 19 | not selected
DC-25 | L4 Control (decides) | G2 Catalogue check | Code | Every product ID exists in catalogue | Accept unknown IDs | P0 | 2 | not selected
DC-26 | L4 Control (decides) | G4 Output schema validator | Code | JSON schema check, max. 2 retries, fallback 'ask staff' | Pass invalid output | P0 | 2 | not selected
DC-27 | L4 Control (decides) | Input sanitiser / injection guard | Code | Treat text, transcripts, OCR, product data as data | Execute embedded instructions | P0 | 2 | not selected
DC-28 | L4 Control (decides) | Basket & alternatives calculator | Code | Totals, pack quantities, cheaper/premium alternatives | Show misleading totals | P0, P2 | 3 | not selected
DC-29 | L4 Control (decides) | Owned-item reconciler | Code | Deduct only confirmed suitable owned items | Treat uncertain items as suitable | P0 | 2 | not selected
DC-30 | L5 Data | Product catalogue | Data | product_catalogue.csv (mock) | Contain logic | P0 | 4 | not selected
DC-31 | L5 Data | Store map / placement | Data | store_map.csv: aisle, shelf, qty, revision | Hold unverified aisles | P0, P1 | 5 | not selected
DC-32 | L5 Data | Project templates | Data | Required facts, questions, BOM roles, quantity rules, review status | Be used if not reviewed | P0 | 7 | not selected
DC-33 | L5 Data | Manufacturer / system data | Data | System ratings, warnings, manuals (mock until verified) | Be overridden by AI | P0 | 5 | not selected
DC-34 | L5 Data | Evidence log | Data | Rule, inputs, source, time per check | Be skipped | P0 | 4 | not selected
DC-35 | L5 Data | Stock & price source adapter | Data | Mock now; retailer API later; timestamps | Present mock as live | P0, P1 | 5 | not selected
DC-36 | Cross-cutting | Labelling & i18n | Code | DE/EN texts, metric/EUR, AI notice, mock labels | Mix units | P0 | 2 | not selected
DC-37 | Cross-cutting | Security & privacy | Code | API key off client, no login, data minimisation, retention, rate limits | Send unnecessary personal data | P0 | 2 | not selected
DC-38 | Cross-cutting | Observability & monitoring | Code | Log escalations, failures, latency, cost | Log personal data unredacted | P0 | 1 | not selected
DC-39 | Cross-cutting | Accessibility & mobile layout | UI | Contrast, scalable text, screen-reader labels, one-hand use | Rely on map only | P0 | 2 | not selected
DC-40 | Cross-cutting | Retailer integration | Code | Hand-off links, reservation (approved), associate sharing | Imply purchase/reservation | P0, P1, P2 | 5 | not selected
DC-41 | Cross-cutting | Template & safety review process | Process | Human review/approval of templates and RB tests | Release unreviewed mounting guidance | P0 | 2 | not selected
Source priority = P-levels of the linked requirements in the requirements file (P0 MVP, P1 pilot, P2 later); highest first.
Layers
| L1 Presentation | Mobile web UI the customer sees
| L2 Application | Orchestration, project state, persistence
| L3 AI (proposes) | LLM agents: classify, extract, phrase, propose – never decide
| L4 Control (decides) | Deterministic code: gates G0–G4, rule engine – decides safety, products, quantities
| L5 Data | Catalogue, store map, templates, manufacturer data, evidence log
| Cross-cutting | Language, security/privacy, monitoring, accessibility, integration, review process

## M1 Traceability
Method 1 – Traceability matrix (requirement × design component)
● = component implements or supports the requirement
|  | L1 | L1 | L1 | L1 | L1 | L1 | L1 | L1 | L1 | L1 | L1 | L1 | L2 | L2 | L2 | L2 | L3 | L3 | L3 | L3 | L3 | L4 | L4 | L4 | L4 | L4 | L4 | L4 | L4 | L5 | L5 | L5 | L5 | L5 | L5 | Cross-cutting | Cross-cutting | Cross-cutting | Cross-cutting | Cross-cutting | Cross-cutting
ID | Type | DC-01 | DC-02 | DC-03 | DC-04 | DC-05 | DC-06 | DC-07 | DC-08 | DC-09 | DC-10 | DC-11 | DC-12 | DC-13 | DC-14 | DC-15 | DC-16 | DC-17 | DC-18 | DC-19 | DC-20 | DC-21 | DC-22 | DC-23 | DC-24 | DC-25 | DC-26 | DC-27 | DC-28 | DC-29 | DC-30 | DC-31 | DC-32 | DC-33 | DC-34 | DC-35 | DC-36 | DC-37 | DC-38 | DC-39 | DC-40 | DC-41
FR-01 | Functional | [12 empty] | ● | ● | ●
FR-02 | Functional | ● | [7 empty] | ● | [7 empty] | ● |  |  |  | ●
FR-03 | Functional |  | ● | [14 empty] | ● |  |  |  | ●
FR-04 | Functional |  | ● | [20 empty] | ● | [5 empty] | ●
FR-05 | Functional |  |  | ● | [14 empty] | ● |  |  |  |  | ● | [8 empty] | ●
FR-06 | Functional |  |  |  | ● | [14 empty] | ● |  |  |  |  | ● | [7 empty] | ●
FR-07 | Functional |  | ● | [26 empty] | ●
FR-08 | Functional | [23 empty] | ● | ● |  |  |  |  | ●
FR-09 | Functional | [23 empty] | ● | [8 empty] | ● | ●
FR-10 | Functional |  |  |  | ● | [15 empty] | ● | [13 empty] | ●
FR-11 | Functional |  |  |  | ● | [26 empty] | ● |  |  |  | ●
FR-12 | Functional |  |  |  | ● | [19 empty] | ● |  |  |  | ●
FR-13 | Functional | [11 empty] | ● | [27 empty] | ●
FR-14 | Functional | [5 empty] | ● | [8 empty] | ●
FR-15 | Functional |  |  |  |  | ● | [8 empty] | ● | [7 empty] | ●
FR-16 | Functional | [7 empty] | ● | [23 empty] | ● | ●
FR-17 | Functional | [6 empty] | ●
FR-18 | Functional |  |  |  | ● | [26 empty] | ● |  |  |  | ●
FR-19 | Functional | [10 empty] | ● |  |  |  |  | ● | [7 empty] | ●
FR-20 | Functional | [7 empty] | ● | [5 empty] | ● |  | ●
FR-21 | Functional | [39 empty] | ●
FR-22 | Functional | [6 empty] | ● | [32 empty] | ●
FR-23 | Functional | [23 empty] | ● |  |  |  | ● | [11 empty] | ●
FR-24 | Functional | [9 empty] | ● | [6 empty] | ●
SR-01 | Safety |  | ● | [11 empty] | ● | [8 empty] | ●
SR-02 | Safety | [20 empty] | ● |  | ● | ●
SR-03 | Safety | [22 empty] | ● | ● | [7 empty] | ●
SR-04 | Safety | [23 empty] | ● | [8 empty] | ●
SR-05 | Safety |  |  |  |  | ● | [18 empty] | ●
SR-06 | Safety |  |  |  |  | ● | [8 empty] | ● | [8 empty] | ●
SR-07 | Safety |  |  |  | ● | [19 empty] | ● | [8 empty] | ●
SR-08 | Safety | [13 empty] | ● |  | ● | [7 empty] | ●
SR-09 | Safety |  |  |  |  | ● | [16 empty] | ●
SR-10 | Safety | [31 empty] | ● | [8 empty] | ●
NFR-01 | Non-functional | ● |  |  | ● | [34 empty] | ●
NFR-02 | Non-functional | [12 empty] | ● | [10 empty] | ● | [5 empty] | ●
NFR-03 | Non-functional | [12 empty] | ● | ● | [11 empty] | ●
NFR-04 | Non-functional | [36 empty] | ●
NFR-05 | Non-functional |  | ● |  | ● | [31 empty] | ●
NFR-06 | Non-functional | [36 empty] | ●
NFR-07 | Non-functional | [16 empty] | ● | [9 empty] | ●
NFR-08 | Non-functional | [38 empty] | ●
NFR-09 | Non-functional | [16 empty] | ● | ● | [17 empty] | ●
NFR-10 | Non-functional | [29 empty] | ● |  | ● |  |  | ●
NFR-11 | Non-functional | [33 empty] | ● |  |  |  | ●
DR-01 | Data | [29 empty] | ●
DR-02 | Data | [30 empty] | ● |  |  |  | ●
DR-03 | Data | [30 empty] | ●
DR-04 | Data | [31 empty] | ● | [8 empty] | ●
DR-05 | Data | [16 empty] | ● | [8 empty] | ●
DR-06 | Data | [6 empty] | ●
DR-07 | Data | [33 empty] | ●
RB-01 | Release-blocking test | [22 empty] | ● | ●
RB-02 | Release-blocking test | [8 empty] | ● | [11 empty] | ● |  | ●
RB-03 | Release-blocking test | [23 empty] | ● | ●
RB-04 | Release-blocking test | [15 empty] | ● | [7 empty] | ●
RB-05 | Release-blocking test |  |  |  | ● | [30 empty] | ●
RB-06 | Release-blocking test |  |  |  | ● | [26 empty] | ●
RB-07 | Release-blocking test |  |  |  |  | ● | [18 empty] | ●
RB-08 | Release-blocking test | [23 empty] | ● | [8 empty] | ●
RB-09 | Release-blocking test | [26 empty] | ●
RB-10 | Release-blocking test | [39 empty] | ●
RB-11 | Release-blocking test | [11 empty] | ●
RB-12 | Release-blocking test | [5 empty] | ●
RB-13 | Release-blocking test | [23 empty] | ● |  |  |  | ●
RB-14 | Release-blocking test | [10 empty] | ● |  |  |  |  | ●
Count |  | 2 | 5 | 1 | 10 | 5 | 2 | 3 | 2 | 2 | 1 | 2 | 2 | 3 | 7 | 2 | 5 | 6 | 2 | 1 | 1 | 4 | 2 | 8 | 19 | 2 | 2 | 2 | 3 | 2 | 4 | 5 | 7 | 5 | 4 | 5 | 2 | 2 | 1 | 2 | 5 | 2

## M2 Proposal
Method 2 – Proposed release & MoSCoW per requirement
Proposal by Claude for team review · change via 'Team decision' column
ID | Type | Category | Requirement | Proposed release | MoSCoW (in that release) | Rationale | Design components (for the part in the proposed release) | Release no. | Team decision | Team comment
FR-01 | Functional | Project lifecycle | Create, save, resume and delete a project | R1 | Should | Session-only save is enough for the demo; full persistence in R2 | DC-13, DC-14, DC-15 | 1
FR-02 | Functional | Project entry | Accept a free-text project description and multiple role-labelled photos | R1 | Must | R1 = free text only (core of UC-1). Photo part moves to R3 (adds most safety/privacy work) | DC-01, DC-17 | 1
FR-03 | Functional | Project entry | Classify project intent and extract candidate objects/visible labels | R1 | Must | Intent classification from text is the entry to the flow. Photo object extraction in R3 | DC-17, DC-02 | 1
FR-04 | Functional | Clarification & facts | Capture measurements, units, constraints and owned items | R1 | Must | Confirmed load and wall type are safety-critical. Owned-item part covered by FR-07 (R2) | DC-02, DC-23 | 1
FR-05 | Functional | Clarification & facts | Ask dependency-aware follow-up questions | R1 | Must | Questions are how missing safety facts are collected | DC-03, DC-18, DC-23, DC-32 | 1
FR-06 | Functional | Planning | Generate a structured bill of materials (BOM) | R1 | Must | The shopping list is the core product value | DC-19, DC-24, DC-32, DC-04 | 1
FR-07 | Functional | Planning | Reconcile suitable owned items against the BOM | R2 | Should | Valuable (problem P2) but not needed for a safe first flow | DC-29, DC-02 | 2
FR-08 | Functional | Validation | Match exact catalogue products and variants | R1 | Must | Zero hallucinated products is a KPI | DC-25, DC-24, DC-30 | 1
FR-09 | Functional | Validation | Validate product and component compatibility | R1 | Must | Compatibility is the main differentiator (problem P1) | DC-24, DC-33, DC-34 | 1
FR-10 | Functional | Validation | Explain recommendations and unresolved facts | R2 | Must | R1 shows the quantity basis/rule ID; full explanations in R2 | DC-20, DC-04, DC-34 | 2
FR-11 | Functional | Shopping | Show price, availability and store information | R1 | Must | Price, stock, aisle with mock labels - needed for the in-store use case | DC-04, DC-31, DC-35 | 1
FR-12 | Functional | Shopping | Offer feasible basket options and alternatives | R2 | Should | Needs the core rule engine first | DC-28, DC-24, DC-04 | 2
FR-13 | Functional | Shopping | Support store search and retailer hand-off | R3 | Should | Needs real store data / partner | DC-12, DC-40 | 3
FR-14 | Functional | Shopping | Provide an offline project checklist | R2 | Should | R1 has simple tick-off; offline PWA in R2 | DC-06, DC-15 | 2
FR-15 | Functional | Safety UX | Present safety stops and escalation | R1 | Must | Safety stops are non-negotiable | DC-05, DC-22, DC-14 | 1
FR-16 | Functional | Assembly | Link assembly steps to reviewed sources | R2 | Should | Needs reviewed manufacturer sources | DC-08, DC-33, DC-32 | 2
FR-17 | Functional | Shopping | Export and share a project summary | R2 | Could | Nice for sharing, low risk | DC-07 | 2
FR-18 | Functional | Shopping | Show verified aisle/zone/rack locations | R3 | Should | Needs verified branch map; R1 uses mock aisle via FR-11 | DC-31, DC-35, DC-04 | 3
FR-19 | Functional | Shopping | Scan products during shopping | R3 | Could | Needs scanner and live product data | DC-11, DC-16, DC-24 | 3
FR-20 | Functional | Assembly | Track assembly and deviations | R3 | Could | Depends on assembly guide (FR-16) | DC-08, DC-16, DC-14 | 3
FR-21 | Functional | Integration | Support an approved reservation integration | Beyond | Won't | Requires retailer contract and API | DC-40 | 4
FR-22 | Functional | Integration | Share a summary with a store associate | R3 | Should | Pilot feature with store associates | DC-07, DC-40 | 3
FR-23 | Functional | Integration | Optimise baskets across retailers | Beyond | Won't | Multi-retailer data not available | DC-28, DC-40, DC-24 | 4
FR-24 | Functional | Project entry | Add voice interaction or room visualisation | R3 | Could | Voice as optional entry; visualisation beyond R3 | DC-10, DC-17 | 3
SR-01 | Safety | Evidence | Separate visual guesses from user-confirmed facts and manufacturer-supported specifications. | R1 | Must | Fact status drives every safety gate | DC-02, DC-14, DC-23 | 1
SR-02 | Safety | Evidence | Never certify wall type, allowable load, concealed services or safe drilling locations from photos. A detector's negative result is not clearance to drill. | R1 | Must | R1: detector-limit part. Photo part becomes testable in R3 | DC-23, DC-24 | 1
SR-03 | Safety | Mounting gate | Require confirmed substrate, fixing system, bracket geometry, intended loading and applicable installation conditions before a final mounting recommendation. | R1 | Must | Core mounting gate for UC-1 | DC-23, DC-24, DC-32 | 1
SR-04 | Safety | Mounting gate | Do not calculate shelf capacity by adding nominal anchor ratings; rely on applicable system evidence or refer to a qualified person. | R1 | Must | Rule engine design decision from day 1 | DC-24, DC-33 | 1
SR-05 | Safety | Drilling | Describe detector capabilities and limitations for relevant hazards; do not imply every detector finds every pipe, especially plastic pipes. | R1 | Must | Every drilling list needs the detector warning | DC-24, DC-05 | 1
SR-06 | Safety | Fail-safe | Inconclusive or missing evidence triggers a stop, not permission to proceed. | R1 | Must | Fail-safe principle | DC-23, DC-14, DC-05 | 1
SR-07 | Safety | Evidence | Preserve manufacturer warnings, installation conditions and approved combinations; generated text cannot weaken them. | R1 | Must | Catalogue safety_note shown; manuals added in R2 | DC-33, DC-24, DC-04 | 1
SR-08 | Safety | Revalidation | Re-run safety and compatibility checks after changes to material, dimensions, load or product. | R1 | Must | User can edit load/wall type -> must revalidate | DC-16, DC-14, DC-24 | 1
SR-09 | Safety | Scope | Exclude high-risk work from the supported flow and provide an appropriate professional hand-off. | R1 | Must | 100 % refusal KPI | DC-22, DC-05 | 1
SR-10 | Safety | Governance | Qualified reviewers approve project templates and release-blocking test cases before public mounting guidance. | R1 | Should | R1: team review of mock templates. R3: qualified expert review (Must) | DC-41, DC-32 | 1
NFR-01 | Non-functional | Usability | Mobile-first; core flow completable in under two minutes in usability testing without instructions. | R1 | Must | In-store, one-hand use is the product context | DC-01, DC-04, DC-39 | 1
NFR-02 | Non-functional | Performance | Catalogue lookup under one second; bounded MVP list generation under five seconds. For a multi-step pilot plan, show progress and target under 60 s at p95. | R1 | Should | < 5 s list target; p95 pilot target in R3 | DC-13, DC-24, DC-30 | 1
NFR-03 | Non-functional | Reliability | If the model fails, offer predefined project templates; recover partial state. Do not proceed when a required validation service fails. | R1 | Must | Template fallback keeps the demo safe if the AI fails | DC-13, DC-26, DC-14 | 1
NFR-04 | Non-functional | Privacy | GDPR principles; no mandatory login; minimise personal data sent to model providers; document retention, deletion and vendor handling. | R1 | Must | GDPR basics; no login | DC-37 | 1
NFR-05 | Non-functional | Transparency | Label AI-generated guidance; distinguish estimates, confirmed facts and verified specifications. Quantities are estimates unless validated. | R1 | Must | EU AI Act transparency notice | DC-04, DC-02, DC-36 | 1
NFR-06 | Non-functional | Security | Encryption, least privilege, upload scanning, tenant isolation, rate limits and redacted logs; restrict tools and outbound domains. | R1 | Should | R1: API key off client, rate limit. Full security in R3 | DC-37 | 1
NFR-07 | Non-functional | Untrusted input | Treat retailer pages, uploaded images, OCR text and manuals as data, never as instructions to the system. | R1 | Must | Prompt-injection resistance is a release-blocking case | DC-27, DC-17 | 1
NFR-08 | Non-functional | Accessibility | Accessible contrast, scalable text, screen-reader labels and a non-map shopping route. | R2 | Should | Basic contrast in R1; full accessibility in R2 | DC-39 | 2
NFR-09 | Non-functional | Language | German and English; metric consistency and dimensional calculations tested in both. | R1 | Should | German default + English toggle; bilingual test suite in R2 | DC-36, DC-17, DC-18 | 1
NFR-10 | Non-functional | Maintainability | Catalogue and project-template data separate from code and replaceable by authorised APIs/feeds. | R1 | Must | Already given by CSV data; keep it | DC-30, DC-32, DC-35 | 1
NFR-11 | Non-functional | Observability | Track unsupported requests, escalations, incidents, source failures, latency and cost per completed project. | R3 | Should | Needed for the pilot, not for the demo | DC-38, DC-34 | 3
DR-01 | Data | Catalogue | Product catalogue: curated mock JSON/CSV (~150-300 products across 5-10 project types); later authorised retailer PIM/API. | R1 | Must | Use existing 70-product CSV; extend in R2 | DC-30 | 1
DR-02 | Data | Stock & price | Stock and price: static, clearly labelled mock values; later timestamped inventory source with agreed freshness policy. | R1 | Must | Mock price/stock, labelled | DC-35, DC-31 | 1
DR-03 | Data | Store layout | Store layout: one store with aisle/zone values only if verified; later branch-specific planogram source. | R1 | Must | Mock store map exists | DC-31 | 1
DR-04 | Data | Templates | Project templates: 5-10 reviewed templates with explicit quantity rules. | R1 | Must | R1: 2 templates (hang shelf, hang picture). R2: 5-10 | DC-32, DC-41 | 1
DR-05 | Data | Model | Model: commercial multimodal model for bounded intent/extraction and clarification; schema-validated outputs. | R1 | Must | Schema-validated model output | DC-17, DC-26 | 1
DR-06 | Data | Sharing | Sharing: link or PDF export; later retailer hand-off. | R2 | Could | Follows FR-17 | DC-07 | 2
DR-07 | Data | Evidence | Evidence registry: source and retrieval time for curated records; later version, licence and lineage. | R1 | Should | Simple evidence record per check; extended in R2 | DC-34 | 1
RB-01 | Release-blocking test | Safety | Unknown wall substrate blocks final anchor selection. | R1 | Must | Gate for UC-1 | DC-23, DC-24 | 1
RB-02 | Release-blocking test | Safety | Photo without scale does not produce exact dimensions. | R3 | Must | Photo arrives in R3 | DC-09, DC-21, DC-23 | 3
RB-03 | Release-blocking test | Compatibility | Similar-looking but wrong screw/variant is detected or remains unresolved. | R1 | Must | Compatibility core | DC-24, DC-25 | 1
RB-04 | Release-blocking test | Safety | Increased intended load invalidates affected fixing decisions. | R1 | Must | Follows SR-08 | DC-16, DC-24 | 1
RB-05 | Release-blocking test | Data | Stale stock is labelled stale and offers a verification path. | R2 | Must | Stock freshness logic in R2 | DC-35, DC-04 | 2
RB-06 | Release-blocking test | Data | Missing map data never produces a fabricated aisle. | R1 | Must | No invented aisle | DC-31, DC-04 | 1
RB-07 | Release-blocking test | Safety | Detector limits do not create false clearance for drilling. | R1 | Must | Detector warning | DC-24, DC-05 | 1
RB-08 | Release-blocking test | Safety | Manufacturer manual wins if it conflicts with generated text. | R1 | Must | Follows SR-07 | DC-33, DC-24 | 1
RB-09 | Release-blocking test | Security | Malicious instructions embedded in product data are ignored as instructions. | R1 | Must | Follows NFR-07 | DC-27 | 1
RB-10 | Release-blocking test | Integration | Retried checkout/reservation action cannot create duplicates. | Beyond | Won't | Reservation not in scope | DC-40 | 4
RB-11 | Release-blocking test | Shopping | Denied location permission leaves postcode search available. | R3 | Must | Store search arrives in R3 | DC-12 | 3
RB-12 | Release-blocking test | Offline | Network loss leaves saved checklist readable and removes live-stock certainty. | R2 | Must | Offline checklist arrives in R2 | DC-06 | 2
RB-13 | Release-blocking test | Compatibility | Ambiguous pack quantity prevents a misleading basket total. | R1 | Must | Basket total in R1 | DC-24, DC-28 | 1
RB-14 | Release-blocking test | Revalidation | A changed product during shopping triggers revalidation of affected assembly steps. | R3 | Must | Scanner arrives in R3 | DC-11, DC-16 | 3

## M2 Components by Release
Method 2 – Which design components are built in which release
Calculated from M2 Proposal · 'First needed in' = earliest release of any linked requirement
ID | Layer | Component | Type | First needed in | # reqs R1 | # reqs R2 | # reqs R3 | # reqs Beyond | What is built when
DC-01 | L1 Presentation | Project entry screen (text + template picker) | UI | R1 | 2 | 0 | 0 | 0 | R1 text + 2 templates · R2 5-10 templates
DC-02 | L1 Presentation | Project summary & fact confirmation | UI | R1 | 4 | 1 | 0 | 0 | R1 load/wall type confirm · R2 owned items · R3 photo facts
DC-03 | L1 Presentation | Clarification question UI | UI | R1 | 1 | 0 | 0 | 0
DC-04 | L1 Presentation | BOM / shopping list view | UI | R1 | 6 | 3 | 1 | 0 | R1 list with mock labels · R2 explanations, alternatives · R3 verified aisles
DC-05 | L1 Presentation | Safety banner & hand-off UI | UI | R1 | 5 | 0 | 0 | 0
DC-06 | L1 Presentation | Checklist & offline cache (PWA) | UI | R2 | 0 | 2 | 0 | 0
DC-07 | L1 Presentation | Export / share module | UI | R2 | 0 | 2 | 1 | 0
DC-08 | L1 Presentation | Assembly guide view | UI | R2 | 0 | 1 | 1 | 0
DC-09 | L1 Presentation | Photo capture & role labelling | UI | R3 | 0 | 0 | 1 | 0
DC-10 | L1 Presentation | Voice input (speech-to-text) | UI | R3 | 0 | 0 | 1 | 0
DC-11 | L1 Presentation | Barcode / product scanner | UI | R3 | 0 | 0 | 2 | 0
DC-12 | L1 Presentation | Store search (postcode / location) | UI | R3 | 0 | 0 | 2 | 0
DC-13 | L2 Application | Orchestrator / flow controller | Code | R1 | 3 | 0 | 0 | 0 | R1 fixed pipeline G0→G4 · R3 backend hardening
DC-14 | L2 Application | Project state machine | Code | R1 | 6 | 0 | 1 | 0
DC-15 | L2 Application | Project persistence | Code | R1 | 1 | 1 | 0 | 0 | R1 session only · R2 local save · R3 backend
DC-16 | L2 Application | Revalidation trigger | Code | R1 | 2 | 0 | 3 | 0
DC-17 | L3 AI (proposes) | Intake agent | AI | R1 | 5 | 0 | 1 | 0 | R1 text intake · R3 photo/voice input
DC-18 | L3 AI (proposes) | Clarification agent | AI | R1 | 2 | 0 | 0 | 0
DC-19 | L3 AI (proposes) | Planner agent | AI | R1 | 1 | 0 | 0 | 0
DC-20 | L3 AI (proposes) | Explanation generator | AI | R2 | 0 | 1 | 0 | 0
DC-21 | L3 AI (proposes) | Vision extraction agent | AI | R3 | 0 | 0 | 1 | 0
DC-22 | L4 Control (decides) | G0 Scope / high-risk filter | Code | R1 | 2 | 0 | 0 | 0
DC-23 | L4 Control (decides) | G1 Required-facts check | Code | R1 | 7 | 0 | 1 | 0
DC-24 | L4 Control (decides) | Rule engine (R-01...R-16) | Code | R1 | 16 | 1 | 1 | 1 | R1 rules R-01…R-16 (mock limits) · R2 alternatives, manuals · R3 reviewed limits
DC-25 | L4 Control (decides) | G2 Catalogue check | Code | R1 | 2 | 0 | 0 | 0
DC-26 | L4 Control (decides) | G4 Output schema validator | Code | R1 | 2 | 0 | 0 | 0
DC-27 | L4 Control (decides) | Input sanitiser / injection guard | Code | R1 | 2 | 0 | 0 | 0
DC-28 | L4 Control (decides) | Basket & alternatives calculator | Code | R1 | 1 | 1 | 0 | 1
DC-29 | L4 Control (decides) | Owned-item reconciler | Code | R2 | 0 | 1 | 0 | 0
DC-30 | L5 Data | Product catalogue | Data | R1 | 4 | 0 | 0 | 0
DC-31 | L5 Data | Store map / placement | Data | R1 | 4 | 0 | 1 | 0
DC-32 | L5 Data | Project templates | Data | R1 | 6 | 1 | 0 | 0 | R1 2 templates · R2 5-10 templates · R3 expert-reviewed
DC-33 | L5 Data | Manufacturer / system data | Data | R1 | 4 | 1 | 0 | 0 | R1 catalogue safety_note · R2 manuals/system ratings
DC-34 | L5 Data | Evidence log | Data | R1 | 2 | 1 | 1 | 0 | R1 rule + inputs + time · R2 sources/versions
DC-35 | L5 Data | Stock & price source adapter | Data | R1 | 3 | 1 | 1 | 0 | R1 static mock · R2 freshness/stale · R3 retailer API
DC-36 | Cross-cutting | Labelling & i18n | Code | R1 | 2 | 0 | 0 | 0 | R1 DE default + EN toggle · R2 bilingual tests
DC-37 | Cross-cutting | Security & privacy | Code | R1 | 2 | 0 | 0 | 0 | R1 key off client, no login · R3 full security review
DC-38 | Cross-cutting | Observability & monitoring | Code | R3 | 0 | 0 | 1 | 0
DC-39 | Cross-cutting | Accessibility & mobile layout | UI | R1 | 1 | 1 | 0 | 0
DC-40 | Cross-cutting | Retailer integration | Code | R3 | 0 | 0 | 2 | 3
DC-41 | Cross-cutting | Template & safety review process | Process | R1 | 2 | 0 | 0 | 0 | R1 team review · R3 qualified expert review

## Roadmap Components
Roadmap – design components per release with priority
Priority = MoSCoW within the release · Source = P-level of the requirements served (P0 MVP, P1 pilot, P2 later)
Release | Layer | Component ID | Component | What this release builds | Priority (MoSCoW) | Source priority
R1 | L1 Presentation | DC-01 | Project entry screen | Text field + 2 template buttons | Must | P0
R1 | L1 Presentation | DC-02 | Fact confirmation view | Shows understood facts; user confirms or edits | Must | P0
R1 | L1 Presentation | DC-03 | Clarification question UI | Max. 3 questions, skip allowed | Must | P0
R1 | L1 Presentation | DC-04 | Shopping list view | BOM with price, stock, aisle, mock and AI labels | Must | P0
R1 | L1 Presentation | DC-05 | Safety banner & hand-off | Refusal, blocked state, detector warning | Must | P0
R1 | Cross-cutting | DC-39 | Mobile layout | One-hand layout, basic contrast | Must | P0
R1 | L2 Application | DC-13 | Orchestrator | Fixed pipeline G0 → intake → G1 → planner → rule engine → G2 → G4 | Must | P0
R1 | L2 Application | DC-14 | Project state machine | Draft … Products validated; Safety blocked; Data unavailable | Must | P0
R1 | L2 Application | DC-16 | Revalidation trigger | Fact change invalidates the list | Must | P0
R1 | L2 Application | DC-15 | Session persistence | Project kept for the session | Should | P0
R1 | L3 AI (proposes) | DC-17 | Intake agent | Classifies intent, extracts candidate facts (text) | Must | P0
R1 | L3 AI (proposes) | DC-18 | Clarification agent | Phrases the questions in DE/EN | Must | P0
R1 | L3 AI (proposes) | DC-19 | Planner agent | Proposes BOM roles only, no products | Must | P0
R1 | L4 Control (decides) | DC-22 | G0 High-risk filter | Electrical, gas, load-bearing, plumbing, roof → refuse | Must | P0
R1 | L4 Control (decides) | DC-23 | G1 Required-facts check | Wall type and load confirmed before mounting output | Must | P0
R1 | L4 Control (decides) | DC-24 | Rule engine R-01…R-16 | Variants, quantities, compatibility, limits (mock values) | Must | P0
R1 | L4 Control (decides) | DC-25 | G2 Catalogue check | Unknown product IDs blocked | Must | P0
R1 | L4 Control (decides) | DC-26 | G4 Output schema validator | Retry max. 2, then 'Please ask store staff' | Must | P0
R1 | L4 Control (decides) | DC-27 | Input sanitiser | Prompt-injection guard | Must | P0
R1 | L4 Control (decides) | DC-28 | Basket total | Sum and pack quantities; ambiguous pack → no total | Must | P0
R1 | L5 Data | DC-30 | Product catalogue | Existing CSV (70 products) | Must | P0
R1 | L5 Data | DC-31 | Store map | Existing CSV (aisle, shelf, quantity) | Must | P0
R1 | L5 Data | DC-32 | Project templates | 2 JSON templates with required facts and quantity rules | Must | P0
R1 | L5 Data | DC-33 | Manufacturer data | Catalogue safety_note and load fields (mock) | Must | P0
R1 | L5 Data | DC-34 | Evidence log | Rule, inputs, time per check | Should | P0
R1 | Cross-cutting | DC-36 | Labelling & i18n | AI notice, mock labels, DE/EN, metric, EUR | Must | P0
R1 | Cross-cutting | DC-37 | Security & privacy | API key server-side, no login, minimal data to the model | Must | P0
R1 | Cross-cutting | DC-41 | Review process | Team review of templates and rule limits | Should | P0
R2 | L3 AI (proposes) | DC-20 | Explanation generator | Turns evidence records into plain-language reasons | Must | P0
R2 | L1 Presentation | DC-04 | Shopping list view | Explanations, alternatives, owned-item marks | Must | P0
R2 | L1 Presentation | DC-06 | Checklist & offline cache (PWA) | Service worker, local save, stale labels | Must | P0
R2 | L5 Data | DC-35 | Stock & price adapter | Timestamps and freshness / stale logic | Must | P0
R2 | L5 Data | DC-32 | Templates and catalogue | 5–10 templates, extended catalogue (DC-30) | Must | P0
R2 | L4 Control (decides) | DC-24 | Rule engine | Rules for new templates; manufacturer system ratings | Must | P0
R2 | L5 Data | DC-34 | Evidence log | Source and version per record | Must | P0
R2 | Cross-cutting | DC-36 | Labelling & i18n | Bilingual test suite (DE/EN) | Must | P0
R2 | L4 Control (decides) | DC-29 | Owned-item reconciler | Deducts only confirmed suitable items | Should | P0
R2 | L4 Control (decides) | DC-28 | Alternatives calculator | Finds compatible cheaper/premium options | Should | P0
R2 | L1 Presentation | DC-08 | Assembly guide view | Steps linked to BOM lines and sources | Should | P0
R2 | L5 Data | DC-33 | Manufacturer / system data | Manuals, warnings, system ratings (mock until verified) | Should | P0
R2 | L2 Application | DC-15 | Persistence | Local save beyond the session | Should | P0
R2 | Cross-cutting | DC-39 | Accessibility | Full screen-reader and contrast support | Should | P0
R2 | L1 Presentation | DC-07 | Export / share module | Link or PDF of selected info | Could | P0
R3 | L1 Presentation | DC-09 | Photo capture & role labelling | Upload with explicit role per photo | Must | P0
R3 | L3 AI (proposes) | DC-21 | Vision extraction agent | Candidate objects and labels from photos | Must | P0
R3 | L4 Control (decides) | DC-23 | G1 Required-facts check | Photo facts stay 'observed' until confirmed | Must | P0
R3 | L1 Presentation | DC-12 | Store search | Postcode and optional location | Must | P0
R3 | Cross-cutting | DC-41 | Review process | Qualified expert approves templates and tests | Must | P0
R3 | L5 Data | DC-35 | Stock & price adapter | Retailer API instead of mock CSV | Should | P1
R3 | L5 Data | DC-31 | Store map / placement | Verified branch planogram | Should | P1
R3 | Cross-cutting | DC-40 | Retailer integration | Hand-off links, associate sharing | Should | P0 / P1
R3 | Cross-cutting | DC-38 | Observability & monitoring | Logs, dashboards, cost per project | Should | P0
R3 | Cross-cutting | DC-37 | Security & privacy | Full review; photo retention rules | Should | P0
R3 | L2 Application | DC-15 | Persistence | Backend storage for pilot projects | Should | P0
R3 | L1 Presentation | DC-11 | Barcode / product scanner | Scan and compare with BOM variant; triggers revalidation (RB-14 only if built) | Could | P1
R3 | L1 Presentation | DC-10 | Voice input | Speech-to-text, editable transcript | Could | P2
Beyond | Cross-cutting | DC-40 | Reservation integration | Approved reservation, no duplicates (FR-21) | Won't | P1
Beyond | L4 Control (decides) | DC-28 | Cross-retailer basket optimisation | FR-23 | Won't | P2
Beyond | L1 Presentation | – | Room visualisation | FR-24 visualisation part | Won't | P2
Components per release by priority
| Release | Must | Should | Could | Won't | Total
| R1 | 25 | 3 | 0 | 0 | 28
| R2 | 8 | 6 | 1 | 0 | 15
| R3 | 5 | 6 | 2 | 0 | 13
| Beyond | 0 | 0 | 0 | 3 | 3

## M2 Release Plan
Method 2 – Release plan, counts and V-model exit gates
All counts are formulas over M2 Proposal / M2 Components by Release
| R1 – MVP / Pitch demo | R2 – Extended MVP | R3 – Pilot-ready
Goal | One safe end-to-end flow: describe project → max. 3 questions → validated shopping list with price, stock, aisle | Make the plan richer and reusable: explanations, alternatives, owned items, offline checklist, assembly guide | Prepare a store pilot: photo & voice entry, real store data, store search, scanner, associate hand-off
Timeframe | 2-week sprint, 19 Oct – ~1 Nov 2026 (built) | After the course (roadmap) | After R2 (roadmap)
Use cases | UC-1 hang 20 kg shelf · UC-3 hang picture/mirror · UC-5 high-risk refusal | + UC-2 freestanding furniture · UC-4 paint a room | + photo-based part identification
Architecture focus | Walking skeleton through all 5 layers: UI, orchestrator, intake/clarification/planner agents, gates G0–G4 + rule engine, CSV data | Widen L1/L4/L5: explanation generator, alternatives calculator, owned-item reconciler, manufacturer data, offline PWA | Add new inputs and integrations: vision agent, voice, scanner, store search, retailer adapter, monitoring, full security
Verification (exit gate) | Release-blocking tests in R1 pass (see count below) + unit tests of rule engine | R1 tests re-run (regression) + R2 tests | All release-blocking tests except Beyond
Validation KPI | 0 % hallucinated products · 100 % high-risk refusal · list < 5 s · ≥ 4/5 users finish in < 2 min | BOM completeness ≥ 90 % on 5-10 templates | Pilot: 50-100 consented projects, variant precision ≥ 95 %
Requirements per release (by type)
Type | R1 | R2 | R3 | Beyond
Functional | 10 | 6 | 6 | 2
Safety | 10 | 0 | 0 | 0
Non-functional | 9 | 1 | 1 | 0
Data | 6 | 1 | 0 | 0
Release-blocking test | 8 | 2 | 3 | 1
Total | 43 | 10 | 10 | 3
MoSCoW per release
MoSCoW | R1 | R2 | R3 | Beyond
Must | 37 | 3 | 3 | 0
Should | 6 | 5 | 4 | 0
Could | 0 | 2 | 3 | 0
Won't | 0 | 0 | 0 | 3
Must share | 86.05% | 30% | 30% | Target ≈ 60 % (DSDM guideline); R1 is higher because safety is fixed Must
Design components first needed (by layer)
Layer | R1 | R2 | R3 | Beyond
L1 Presentation | 5 | 3 | 4 | 0
L2 Application | 4 | 0 | 0 | 0
L3 AI (proposes) | 3 | 1 | 1 | 0
L4 Control (decides) | 7 | 1 | 0 | 0
L5 Data | 6 | 0 | 0 | 0
Cross-cutting | 4 | 0 | 2 | 0
Total | 29 | 5 | 7 | 0